## Tabelle1
Week | <component> | Release
2021-01-25 | kickoff communicating goals and setup
2020-02-01 | setup accounts for azure, guthub, trello
2020-02-08 | setup azure Cloud shell
2020-02-15 | Implement hello world application | 1.0
2020-02-22 | add lint and testautomation
2020-03-01 | configure Github Actions for CI
2020-03-08 | Implement ML app housing prices | 1.1
2020-04-15 | Extend App Flask API | 1.2
2020-03-22 | Implement CD on Azure Devops usinge pipelines
2020-03-29 | User Acceptance test
2020-04-05 | Documentation
2020-04-12 | make Demo Video
| Goals | Goals
functional: predict tion of house prices
non-funct: Web-API Rest service
non-funct: run as Azure App Service
non-funct: CI/CD pipeline using GithubActions and Azure DevOps pipelines